## Task_Table
How to (Not) Train Your Apprentice
[7 empty] | Week 1: Aug 20 | [6 empty] | Week 2: Aug 27 | [6 empty] | Week 3: Sep 3 | [6 empty] | Week 4: Sep 10 | [6 empty] | Week 5: Sep 17 | [6 empty] | Week 6: Sep 24 | [6 empty] | Week 7: Oct 1 | [6 empty] | Week 8: Oct 8 | [6 empty] | Week 9: Oct 15 | [6 empty] | Week 10: Oct 22 | [6 empty] | Week 11: Oct 29 | [6 empty] | Week 12: Nov 5 | [6 empty] | Week 13: Nov 12 | [6 empty] | Week 14: Nov 19 | [6 empty] | Week 15: Nov 26 | [6 empty] | Week 16: Dec 3 | [6 empty] | Week 17: Dec 10
ID | Task Name | Status | Duration | Start | Finish | Resource | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
1 | Class 1 |  | 0 days | Fri Aug 25 | Fri Aug 25 | All
2 | Class 2 |  | 0 days | Fri Sep 1 | Fri Sep 1 | All
3 | Class 3 |  | 0 days | Fri Sep 8 | Sat 1/14/17 | All
4 | Class 4 |  | 0 days | Fri Sep 15 | Thu 1/19/17 | All
5 | Class 5 |  | 0 days | Fri Sep 22 | Thu 1/19/17 | All
6 | Class 6 |  | 0 days | Fri Sep 29 | Thu 1/26/17 | All
7 | Class 7 |  | 0 days | Fri Oct 6 | Sat 1/28/17 | All
8 | Class 8 |  | 0 days | Fri Oct 13 | Thu 1/26/17 | All
9 | Class 9 |  | 0 days | Fri Oct 20 | Sat 1/28/17 | All
10 | Class 10 |  | 0 days | Fri Oct 27 | Sun 1/29/17 | All
11 | Class 11 |  | 0 days | Fri Nov 3 | Mon 2/13/17 | All
12 | Class 12 |  | 0 days | Fri Nov 10 | Mon 2/13/17 | All
13 | Class 13 |  | 0 days | Fri Nov 17 | Mon 2/13/17 | All
14 | Fall Break |  | 9 days | Sat Nov 18 | Sun Nov 26 | None!!!
15 | Class 14 |  | 0 days | Fri Dec 1 | Thu 2/2/17 | All
16 | Research top-down dungeon crawler in Unity |  | 7 days | Fri Aug 25 | Fri Sep 1 | William
17 | Skeleton Unity Project |  | 7 days | Fri Aug 25 | Fri Sep 1 | William
18 | Level Design (Paper Map, floors made in Unity with default textures, basic UI) |  | 22 days | Sun Aug 27 | Sun Sep 17 | All
19 | Character programming, basic mechanics, and basic spritework |  | 13 days | Mon Sep 18 | Sat Sep 30 | All
20 | First Prototype Due (Alpha, Basic Assets, Basic Mechanics) |  | 0 days | Sun Oct 1 | Sun Oct 1 | All
21 | Midterm Milestone Update (Alpha Build) |  | 0 days | Fri Oct 6 | Fri Oct 6 | All
22 | Programming intermediate mechanics (magic types, enchantments, save system, inventory) |  | 28 days |  |  | William
23 | Tile sets for levels, full spritework for player |  | 14 days |  |  | Erica
24 | Spritework for enemies |  | 14 days |  |  | Erica
25 | Spritework for interactive objects |  | 14 days |  |  | Erica
26 | Spritework integration |  | 3 days |  |  | William
27
28
29
30 | Second Prototype Due (Beta, Assets Halfway Done, Advanced Mechanics) |  | 0 days | Wed Nov 1 | Wed Nov 1 | All
31 | Programming advanced mechanics (timing puzzles, boss battle) |  | 14 days |  |  | William
32 | Playtesting as mechanics are done |  | 31 days |  |  | All
33 | Make a build before fall break and play around with it |  | 3 days |  |  | All
34
35
36
37
38 | Do UI art and integrate it |  |  |  |  | All
39 | All remaining spritework done and integrated |  |  |  |  | All
40 | Third Prototype Due (Mostly Done aside from some bugs) |  | 0 days | Fri Dec 1 | Fri Dec 1
41 | Fine-tuning, polishing, and taking care of loose ends |  | 7 days |  |  | All
42 | Extras, secrets, and Easter eggs |  | 7 days |  |  | All
43
44
45
46
47
48
49
50 | Zero Bug Day (NO BUGS IN EXECUTABLE; GAME IS READY; FIRST PLATFORM TEST) |  | 0 days | Fri Dec 8 | Fri Dec 8
51 | Final Platform Test, Final Build |  | 0 days | Sat Dec 9 | Sat 3/4/17 | William
52 | One More Test for Good Measure to Make Sure the Game Runs Well |  | 0 days | Mon Dec 11 | Wed Dec 13 | William
53 | Game Due |  | 0 days | Fri Dec 15 | Fri Dec 15 | All
Notes: | [13 empty] | Revision Notes:
1 | Prototype days are for making sure the game is progressing at a steady pace
2 | We will present the first prototype for the midterm milestone update
3 | All of the hard work happens before Nov 1; after that, it's mostly fine-tuning and cleaning things up
4 | There will be no changes to the mechanics after Nov 1
5 | There will be no changes to the game after Dec 8
Team Members:
1 | Erica Harris |  | Designer
2 | William Howell |  | Programmer
3
4